## VSM Template
Value stream map — template
Shown on screen; each group copies the layout onto paper or a whiteboard.
Fill in the stages the change really went through, left to right.
Change mapped: |  |  |  |  | Group:
The map | Stage 1 | Stage 2 | Stage 3 | Stage 4 | Stage 5 | Stage 6 | Stage 7
Stage name
Process time — someone working on it (days)
Wait time — sitting in a queue (days)
%C/A — next stage could use it as handed over
Totals
Total lead time (all process time + all wait time) | 0
Total process time | 0
Total wait time | 0
Activity ratio (process time / lead time)
Which stage is development? (enter 1–7) | 3
Development process time | 0
Development's share of lead time (dev PT / lead time)
The arithmetic
Coding made faster by | 26%
Development process time made 26% faster | 0
New total lead time | 0
Improvement in lead time
Lowest %C/A on the map
… and where
Hot Spot!!
Longest wait on the map …
… what would it take to halve it?
… what would it take to raise the lowest %C/A?
If faster coding makes more changes, what happens there?

## Worked Examples
For comparison — two worked examples from the opening talk
Neither has %C/A per stage; both have a total first-time-through figure.
| Project team | Product team
Stages | Requirements, design, development, testing, deployment | Discovery, planning, development, validation, release
Lead time (days) | 159 | 19
Process time (days) | 112 | 13
Wait time (days) | 47 | 6
Right first time | 70% | 84%
Development share of lead time | 22% | 10.5%
Coding made faster by | 26%
Development process time (days) | 34.98 | 1.995
Lead time saved by faster coding (days) | 9.0948 | 0.5187
Lead time saved (% of lead time) | 5.72% | 2.73%